## ReserveWell
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Define project goals, scope, objectives and deliverable | 1 | 3 | Resolved | 1 |  | 0 | 8 | <Vision.pdf>
Identify stakeholders, end users | 1 | 3 | Resolved | 1 | Tunalı | 0 | 8 | <Vision.pdf>
Identify and assess potential risks | 1 | 2 | Resolved | 1 | Mustafa | 0 | 5 | <RiskList.pdf>
Develop a business case | 1 | 3 | Closed | 1 |  | 0 | 8 | <Vision.pdf>
Develop a detailed project plan | 1 | 8 | Closed | 1 | Umut | 0 | 22 | <ProjectPlan.pdf>
Define schedules | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Define milestones | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Decide on necessary resources | 1 |  | Closed | 1 |  | 0 | 6
Define prior deployment plan | 1 | 5 | Closed | 1 | Umut | 0 | 13 | <Architecture Notebook.pdf>
Define roles and responsibilities | 2 | 2 | Closed | 2 | Ezgi E. | 0 | 6
Define system-wide requirements | 2 | 3 | Closed | 2 | Mustafa | 0 | 8 | <SystemWideRequirements.pdf>
Develop a use-case models | 2 | 5 | Closed | 2 |  | 0 | 15 | <Use Case Diagram_ReserveWell>
Define and classify actors | 2 | 2 | Closed | 1 |  | 0 | 8
Form use-case diagrams | 1 | 3 | Closed | 2 | Tunalı | 0 | 7
Define diner uses cases | 2 | 13 | Closed | 2 |  | 0 | 29
Register | 2 |  | Closed | 2 |  | 0 | 3 | <UC1_Register(Diner).pdf>
Make Reservation | 2 |  | Closed | 1 | Ezgi E. | 0 | 8 | <UC2_Make Reservation.pdf>
Update Reservation | 2 |  | Closed | 1 | Umut | 0 | 5 | <UC3_Update Reservation(Diner).pdf>
Exit from a Waitlist | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC4_Exit From the Waitlist.pdf>
Make Reservation upon Wishlist Availability | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC5_Make Reservation upon Wishlist Availability.pdf>
Rate the Restaurant | 2 |  | Closed | 2 | Ezgi E. | 0 | 3 | <UC6_Rate the Restaurant.pdf>
Define restaurant manager uses cases | 2 | 13 | Closed | 2 |  | 0 | 41
RegisterR | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <UC7_Register(Restaurant Manager).pdf>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC8_Display Reservations (Restaurant Manager).pdf>
Manage Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC9_Manage Reservations.pdf>
Edit Working Hours | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC10_Edit Working Hours.pdf>
Edit Capacity | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC11_Edit Capacity.pdf>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC12_Display Dashboards.pdf>
Manage Restaurant's Waitlist | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC13_Manage Restaurant's Waitlist.pdf>
Define waitstaff use cases | 2 | 13 | Closed | 2 | Ezgi E. | 0 | 27
Register | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC14_Register (Waitstaff).pdf>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC15_Display Reservations (Waitstaff).pdf>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC12_Display Dashboards.pdf>
Confirm Realized Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC16_Confirm Realized Reservations.pdf>
Define offline scenarios for internet failures | 2 | 3 | Closed (Out of Scope) | 2 |  | 0 | 0
Support basic creating new reservation process | 2 | 8 | Closed | 2 | Umut | 0 | 27
Prototype UI | 2 |  | Closed | 2 | Umut | 0 | 5
Do the design | 2 |  | Closed | 2 | Umut | 0 | 8 | <Design.pdf>
Implement | 2 |  | Closed | 2 | Umut | 0 | 5 | <Implementation.pdf>
Test | 3 |  | Closed | 2 | Umut | 0 | 3 | <TestCases.pdf>, <TestScripts.pdf>
Verify data flow | 2 |  | Closed | 2 | Umut | 0 | 3
Draw sequence diagram to be included in Design Document | 2 |  | Closed | 2 | Umut | 0 | 3 | <Design.pdf>
Define an initial high-level system architecture | 2 | 3 | Closed | 3 | Umut | 0 | 8 | <Architecture Notebook.pdf>
Define objects, attrbiutes, methods | 3 |  | Closed | 3 | Umut | 5 | 5 | <Design.pdf>, <Architecture Notebook.pdf>
Form dataflow diagram | 2 |  | Closed | 2 | Tunalı | 0 | 3
Support basic registering process for diners | 2 | 5 | Closed | 3 | Team | 0 | 20
Prototype UI | 2 |  | Closed | 3 | Team | 0 | 3
Do the design | 2 |  | Closed | 3 | Team | 0 | 5
Implement | 2 |  | Closed | 3 | Team | 0 | 3
Test | 2 |  | Closed | 3 | Team | 0 | 3
Verify data flow | 2 |  | Closed | 3 | Team | 0 | 3
Draw sequence diagram to be included in Design Document | 2 |  | Closed | 3 | Team | 0 | 3 | <Design.pdf>
Support basic registering process for restaurant staff | 2 | 5 | Closed | 3 | Team | 0 | 20
Prototype UI | 2 |  | Closed | 3 | Team | 0 | 3
Do the design | 2 |  | Closed | 3 | Team | 0 | 5
Implement | 2 |  | Closed | 3 | Team | 0 | 3
Test | 2 |  | Closed | 3 | Team | 0 | 3
Verify data flow | 2 |  | Closed | 3 | Team | 0 | 3
Draw sequence diagram to be included in Design Document | 2 |  | Closed | 3 | Team | 0 | 3 | <Design.pdf>
Support restaurant capacity customizations | 2 | 5 | Closed | 3 | Team | 0 | 22
Prototype UI | 2 |  | Closed | 3 | Team | 0 | 3
Do the design | 2 |  | Closed | 3 | Team | 0 | 5
Implement | 2 |  | Closed | 3 | Team | 0 | 3
Test | 2 |  | Closed | 3 | Team | 0 | 3
Verify data flow | 2 |  | Closed | 3 | Team | 0 | 5
Draw sequence diagram to be included in Design Document | 2 |  | Closed | 3 | Team | 0 | 3 | <Design.pdf>
Support reservations display | 2 | 5 | Closed | 4 | Team | 0 | 22
Prototype UI | 2 |  | Closed | 4 | Team | 0 | 3
Do the design | 2 |  | Closed | 4 | Team | 0 | 5
Implement | 2 |  | Closed | 4 | Team | 0 | 3
Test | 2 |  | Closed | 4 | Team | 0 | 3
Verify data flow | 2 |  | Closed | 4 | Team | 0 | 5
Draw sequence diagram to be included in Design Document | 2 |  | Closed | 4 | Team | 0 | 3 | <Design.pdf>
Support restaurant workhours customizations | 2 | 5 | New | 5 | Team | 0 | 22
Prototype UI | 2 |  | New | 5 | Team | 0 | 3
Do the design | 2 |  | New | 5 | Team | 0 | 5
Implement | 2 |  | New | 5 | Team | 0 | 3
Test | 2 |  | New | 5 | Team | 0 | 3
Verify data flow | 2 |  | New | 5 | Team | 0 | 5
Draw sequence diagram to be included in Design Document | 2 |  | New | 5 | Team | 0 | 3
Support basic managing reservations process (restaurant manager) | 3 | 13 | Partial | 4 | Team | 26 | 35
Prototype UI | 3 |  | Partial | 4 | Team | 3 | 5
Do the design | 3 |  | Assigned | 4 | Team | 7 | 8
Implement | 3 |  | Partial | 4 | Team | 6 | 8
Test | 3 |  | Partial | 4 | Team | 2 | 3
Verify data flow | 3 |  | Assigned | 4 | Team | 6 | 8
Draw sequence diagram to be included in Design Document | 3 |  | Assigned | 4 | Team | 2 | 3 | <Design.pdf>
Support basic realizing reservations process (waitstaff) | 3 | 13 | Partial | 4 | Team | 26 | 35
Prototype UI | 3 |  | Assigned | 4 | Team | 3 | 5
Do the design | 3 |  | Assigned | 4 | Team | 7 | 8
Implement | 3 |  | Partial | 4 | Team | 6 | 8
Test | 3 |  | Partial | 4 | Team | 2 | 3
Verify data flow | 3 |  | Assigned | 4 | Team | 6 | 8
Draw sequence diagram to be included in Design Document | 3 |  | Assigned | 4 | Team | 2 | 3
Support waitlist management | 4 | 13 | New | 5 | Team | 32 | 35
Prototype UI | 4 |  | New | 5 | Team | 5 | 5
Do the design | 4 |  | New | 5 | Team | 8 | 8
Implement | 4 |  | New | 5 | Team | 8 | 8
Test | 4 |  | New | 5 | Team | 3 | 3
Verify data flow | 4 |  | New | 5 | Team | 8 | 8
Draw sequence diagram to be included in Design Document | 3 |  | New | 5 | Team | 3 | 3
Support feedback infrastructure | 3 | 8 | New | 5 |  | 23 | 23
Prototype UI | 3 |  | New | 5 |  | 5 | 5
Do the design | 3 |  | New | 5 |  | 5 | 5
Implement | 3 |  | New | 5 |  | 5 | 5
Test | 3 |  | New | 5 |  | 3 | 3
Verify data flow | 3 |  | New | 5 |  | 5 | 5
Support data visualization | 3 | 13 | New | 5 |  | 31 | 31
Decide whether outsourcing or inhouse | 3 |  | Closed | 4 |  | 0 | 8
Prototype UI | 3 |  | New | 5 |  | 5 | 5
Do the design | 3 |  | New | 5 |  | 5 | 5
Implement | 3 |  | New | 5 |  | 5 | 5
Test | 3 |  | New | 5 |  | 3 | 3
Verify data flow | 3 |  | New | 5 |  | 5 | 5
Complete Development Work Products | 2 |  | Verified | 4 |  |  | 28
Define design artifact | 2 |  | Closed | 3 |  |  | 8
Define implementation artifact | 2 |  | Closed | 2 |  |  | 8
Define build artifact | 2 |  | Closed | 4 |  |  | 6
Define developer test artifact | 2 |  | Closed | 4 | Mustafa |  | 6
Create iteration plans | 1 | 8 | Closed | 4 | Ezgi E. | 0 | 24
Define Iteration Plan 1 | 1 |  | Closed | 1 | Ezgi E. | 0 | 6 | <IterationPlan1.pdf>
Define Iteration Plan 2 | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <IterationPlan2.pdf>
Define Iteration Plan 3 | 2 |  | Closed | 3 | Ezgi E. | 0 | 6 | <IterationPlan3.pdf>
Define Iteration Plan 4 | 3 |  | Closed | 4 | Ezgi E. | 0 | 6 | <IterationPlan4.pdf>
Do the design | 2 | 8 | Closed | 4 | Umut | 0 | 22
Develop code | 2 | 13 | Closed | 4 |  | 0 | 29
Design interface | 2 |  | Closed | 3 |  | 0 | 8
Define data base and entity relationships | 2 |  | Closed | 3 |  | 0 | 8 | <Implementation.pdf>
Detailed architecture | 3 |  | Closed | 4 |  | 0 | 13
Collaborate with restaurants to integrate the system with existing systems | 3 | 5 | Assigned | 5 | Umut | 18 | 18
Define data management policies | 4 | 5 | Assigned | 5 | Tunalı | 13 | 13
Ensure compliance with data privacy regulations | 4 | 1 | Assigned | 5 | Tunalı | 5 | 4
Decide on how the info is handled, stored and protected | 4 | 1 | Assigned | 5 | Tunalı | 8 | 4
Define test scenarios which are not use case specific | 2 | 8 | Assigned | 5 | Mustafa | 20 | 20
Involve restaurant staff to validate the system and requirements | 3 | 5 | New | 5 |  | 13 | 13
Collaborate with marketing team to promote the system to potential diners | 5 | 100 | New
Oversee users training by restaurant staff | 5 | 100 | New
Monitor and report performance | 5 | 13 | New |  |  | 29 | 29
Plan for ongoing support and maintenance | 5 | 8 | New |  |  | 21 | 21
Collect feedback about the restaurants from the users | 5 | 8 | New |  |  | 21 | 21
Add additional features according to collected feedback | 5 | 100 | New
Add loyalty program to leverage the platform as a marketing tool | 5 | 100 | New
Add layout support | 5 | 100 | New
Integrate with google maps | 5 | 100 | New