## Sheet1
ReserveWell Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
6 | 2023-02-11 | Scope Creep | Expanding project scope beyond the initial plan | Schedule | 4 | 50% | 2 | Project Managers | Strictly adhere to project scope and goals. Implement a formal change control process for any scope adjustments.
9 | 2023-02-11 | Inability to Collect User Feedback | Challenges in capturing, and acting upon user feedback | Business | 4 | 50% | 2 | Quality Team | Establish clear feedback channels, analyze feedback systematically, and prioritize feature enhancements based on user needs.
2 | 2023-02-11 | Data Security and Privacy | Risks of data breaches and privacy violations | Technical | 5 | 30% | 1.5 | Technical Leads | Implement robust data encryption, access controls, and comply with relevant data protection regulations. Regular security audits.
1 | 2023-02-11 | Technical Skills Limitation | Limited expertise in UI/UX, frontend, and mobile app development | Resource | 4 | 30% | 1.2 | Technical Leads | Invest in training for team members or consider hiring external experts. Collaborate with experienced developers for critical tasks.
4 | 2023-02-11 | Competitive Pressure | Competition from existing reservation systems | Business | 2 | 40% | 0.8 | Project Managers | Focus on unique features, superior user experience, and strong customer support. Continuously analyze and adapt to market changes.
3 | 2023-02-11 | Adoption and User Engagement | Challenges in getting diners and restaurants to adopt the system | Business | 3 | 20% | 0.6 | Product Owner | Develop a marketing and user engagement strategy. Provide incentives for early adopters. Gather and act on user feedback.
5 | 2023-02-11 | Platform Compatibility | Compatibility issues with various web and mobile platforms | Technical | 2 | 30% | 0.6 | Technical Leads | Designing a cross-browser application from start, and thoroughly test and optimize the application for different browsers, operating systems, and devices.
7 | 2023-02-11 | Dependence on Third-party Services | Reliance on external services such as payment gateways | Business | 4 | 10% | 0.4 | Product Owner | Identify reliable third-party services, have backup options, and establish service level agreements to ensure uptime and reliability.
10 | 2023-02-11 | Server and Network Failures | Server and network outages affecting system availability | Technical | 3 | 10% | 0.3 | Technical Leads | Implement redundancy and failover mechanisms. Regularly monitor server and network performance, and have disaster recovery plans.
8 | 2023-02-11 | Regulatory Compliance | Non-compliance with industry regulations and standards | Business | 3 | 5% | 0.15 | Product Owner | Regularly monitor regulatory changes, conduct compliance audits, and adjust the system accordingly.
Note on E2: ====== ID#AAAA_i_X4KQ rbalduino (2023-11-04 07:40:26) Risk Type = Direct or Indirect Resource Business Technical Schedule
Note on F2: ====== ID#AAAA_i_X4KY mbarnard (2023-11-04 07:40:26) Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: ====== ID#AAAA_i_X4Kc mbarnard (2023-11-04 07:40:26) Probability is the percentage chance that a risk will occur.
Note on H2: ====== ID#AAAA_i_X4KU mbarnard (2023-11-04 07:40:26) Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.