## ReserveWell
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Define project goals, scope, objectives and deliverable | 1 | 3 | Resolved | 1 |  | 0 | 8 | <Vision.pdf>
Identify stakeholders, end users | 1 | 3 | Resolved | 1 | Tunalı | 0 | 8 | <Vision.pdf>
Identify and assess potential risks | 1 | 2 | Resolved | 1 | Mustafa | 0 | 5 | <RiskList.pdf>
Develop a business case | 1 | 3 | Closed | 1 |  | 0 | 8 | <Vision.pdf>
Develop a detailed project plan | 1 | 8 | Closed | 1 | Umut | 0 | 22 | <ProjectPlan.pdf>
Define schedules | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Define milestones | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Decide on necessary resources | 1 |  | Closed | 1 |  | 0 | 6
Define prior deployment plan | 1 | 5 | Closed | 1 | Umut | 5 | 13
Define roles and responsibilities | 2 | 2 | Assigned | 2 | Ezgi E. | 2 | 6
Define system-wide requirements | 2 | 3 | Assigned | 2 | Mustafa | 8 | 8 | <SystemWideRequirements.pdf>
Develop a use-case models | 2 | 5 | Closed | 2 |  | 6 | 15 | <Use Case Diagram_ReserveWell>
Define and classify actors | 2 | 2 | Closed | 1 |  | 6 | 8
Form use-case diagrams | 1 | 3 | Closed | 2 | Tunalı | 0 | 6
Define diner uses cases | 2 | 13 | Closed | 2 |  | 11 | 29
Register | 2 |  | Closed | 2 |  |  |  | <UC1_Register(Diner).pdf>
Make Reservation | 2 |  | Closed | 1 | Ezgi E. | 0 | 8 | <UC2_Make Reservation.pdf>
Update Reservation | 2 |  | Closed | 1 | Umut | 0 | 5 | <UC3_Update Reservation(Diner).pdf>
Exit from a Waitlist | 2 |  | Closed | 2 | Ezgi E. | 5 | 5 | <UC4_Exit From the Waitlist.pdf>
Manage Notifications | 2 |  | Closed | 2 | Ezgi E. |  |  | <UC5_Manage Notifications.pdf>
Rate the Restaurant | 2 |  | Closed | 2 | Ezgi E. | 3 | 3 | <UC6_Rate the Restaurant.pdf>
Define restaurant manager uses cases | 2 | 13 | Closed | 2 |  | 0 | 29
RegisterR | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <UC7_Register(Restaurant Manager).pdf>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC8_Display Reservations (Restaurant Manager).pdf>
Manage Reservations - güncelle feedbacke göre | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC9_Manage Reservations.pdf>
Edit Working Hours | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC10_Edit Working Hours.pdf>
Edit Capacity | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC11_Edit Capacity.pdf>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC12_Display Dashboards.pdf>
Manage Restaurant's Waitlist | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC13_Manage Restaurant's Waitlist.pdf>
Define waitstaff use cases | 2 | 13 | Closed | 2 | Ezgi E. | 0 | 27
Register | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC14_Register (Waitstaff).pdf>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC15_Display Reservations (Waitstaff).pdf>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC12_Display Dashboards.pdf>
Confirm Realized Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC16_Confirm Realized Reservations.pdf>
Support basic creating new reservation process | 2 | 8 | Verified | 2 | Umut | 3 | 24
Prototype UI | 2 |  | Closed | 2 | Umut | 0 | 5
Do the design | 2 |  | Closed | 2 | Umut | 0 | 8 | <Design.pdf>
Implement | 2 |  | Closed | 2 | Umut | 0 | 5 | <Implementation.pdf>
Test |  |  | Assigned | 2 | Umut | 3 | 3 | <TestCases.pdf>, <TestScripts.pdf>
Verify data flow | 2 |  | Closed | 2 | Umut | 0 | 3
Define an initial high-level system architecture | 2 | 3 | Verified | 3 |  | 8 | 8 | <Architecture Notebook.pdf>
Define objects, attrbiutes, methods | 3 |  | New | 3 |  | 5 | 5 | <Design.pdf>, <Architecture Notebook.pdf>
Form dataflow diagram | 2 |  | Closed | 2 | Tunalı | 0 | 3
Support basic registering process | 1 | 5 | Assigned | 3 | Tunalı | 17 | 17
Prototype UI | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Do the design | 1 |  | Assigned | 3 | Tunalı | 5 | 5
Implement | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Test |  |  | Assigned | 3 | Tunalı | 3 | 3
Verify data flow | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Support basic managing reservations process | 2 | 13 | Assigned | 3 | Mustafa | 32 | 32
Prototype UI | 2 |  | Assigned | 3 | Mustafa | 5 | 5
Do the design | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Implement | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Test |  |  | Assigned | 3 | Mustafa | 3 | 3
Verify data flow | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Support waitlist management | 2 | 13 | Assigned | 4 | Umut | 32 | 32
Prototype UI | 2 |  | Assigned | 4 | Umut | 5 | 5
Do the design | 2 |  | Assigned | 4 | Umut | 8 | 8
Implement | 2 |  | Assigned | 4 | Umut | 8 | 8
Test |  |  | Assigned | 4 | Umut | 3 | 3
Verify data flow | 2 |  | Assigned | 4 | Umut | 8 | 8
Support restaurant customizations | 2 | 5 | New | 3 |  | 19 | 19
Prototype UI | 2 |  | New | 3 |  | 3 | 3
Do the design | 2 |  | New | 3 |  | 5 | 5
Implement | 2 |  | New | 3 |  | 3 | 3
Test |  |  | New | 3 |  | 3 | 3
Verify data flow | 2 |  | New | 3 |  | 5 | 5
Support feedback infrastructure | 3 | 8 | New | 4 |  | 23 | 23
Prototype UI | 3 |  | New | 4 |  | 5 | 5
Do the design | 3 |  | New | 4 |  | 5 | 5
Implement | 3 |  | New | 4 |  | 5 | 5
Test |  |  | New | 4 |  | 3 | 3
Verify data flow | 3 |  | New | 4 |  | 5 | 5
Support data visualization | 3 | 13 | New | 3 |  | 31 | 31
Decide whether outsourcing or inhouse | 3 |  | New | 2 |  | 8 | 8
Prototype UI | 3 |  | New | 3 |  | 5 | 5
Do the design | 3 |  | New | 3 |  | 5 | 5
Implement | 3 |  | New | 3 |  | 5 | 5
Test |  |  | New | 3 |  | 3 | 3
Verify data flow | 3 |  | New | 3 |  | 5 | 5
Complete Development Work Products | 2 |  | Verified | 3
Define design artifact | 2 |  | Closed | 2
Define implementation artifact | 2 |  | Closed | 2
Define build artifact | 2 |  | New | 3
Define developer test artifact | 2 |  | Assigned | 3 | Mustafa
Create iteration plans | 1 | 8 | Verified | 4 | Ezgi E. | 6 | 24
Define Iteration Plan 1 | 1 |  | Closed | 1 | Ezgi E. | 0 | 6 | <IterationPlan1.pdf> | we have different task categories with different priority subtasks. ...olabildiğince iterationa göre sıraladım ama ana başlıkları sırf altında farkı öncelikli subtasklar var diye ayırmak istemiyorum. Bence bu kadarı yeterli. Zaten work items listi sıralı yapacaksınız diye bir şey bile yok
Define Iteration Plan 2 | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <IterationPlan2.pdf>
Define Iteration Plan 3 | 2 |  | Closed | 3 | Ezgi E. | 0 | 6 | <IterationPlan3.pdf>
Define Iteration Plan 4 | 3 |  | Assigned | 4 | Ezgi E. | 6 | 6
Define test scenarios which are not use case specific | 2 | 8 | Assigned | 4 | Mustafa | 20 | 20
Define offline scenarios for internet failures | 2 | 3 | Closed (Out of Scope) | 2 |  | 8 | 8
Do the design | 2 | 8 | Assigned | 3 | Umut | 22 | 22
Develop code | 2 | 13 | Assigned | 3 |  | 29 | 29
Design interface | 2 |  | New | 3 |  | 8 | 8
Define data base and entity relationships | 2 |  | New | 3 |  | 8 | 8
Detailed architecture | 3 |  | New | 3 |  | 13 | 13
Involve restaurant staff to validate the system and requirements | 3 | 5 | New | 5 |  | 13 | 13
Collaborate with restaurants to integrate the system with existing systems | 3 | 5 | Assigned | 3 | Umut | 18 | 18
Define data management policies | 4 | 5 | Assigned | 4 |  | 13 | 13
Ensure compliance with data privacy regulations | 4 | 1 | Assigned | 4 |  | 5 | 4
Decide on how the info is handled, stored and protected | 4 | 1 | Assigned | 4 |  | 8 | 4
Collaborate with marketing team to promote the system to potential diners | 5 | 100 | New
Oversee users training by restaurant staff | 5 | 100 | New
Monitor and report performance | 5 | 13 | New |  |  | 29 | 29
Plan for ongoing support and maintenance | 5 | 8 | New |  |  | 21 | 21
Collect feedback about the restaurants from the users | 5 | 8 | New |  |  | 21 | 21 |  | bunun onların reviewı anlamında kullanılmadığını anlatmak için user ekledim.
Add additional features according to collected feedback | 5 | 100 | New
Add loyalty program to leverage the platform as a marketing tool | 5 | 100 | New
Add layout support | 5 | 100 | New
Integrate with google maps | 5 | 100 | New