## ReserveWell
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Define project goals, scope, objectives and deliverable | 1 | 3 | Resolved | 1 |  | 0 | 8 | <Vision.doc>
Identify stakeholders, end users | 1 | 3 | Resolved | 1 | Tunalı | 0 | 8 | <Vision.doc>
Identify and assess potential risks | 1 | 2 | Resolved | 1 | Mustafa | 0 | 5 | <RiskList.doc>
Develop a business case | 1 | 3 | Closed | 1 |  | 0 | 8 | <Vision.doc>
Create an iteration plan | 1 | 2 | Closed | 1 | Ezgi E. | 0 | 5 | <IterationPlan.doc>
Develop a detailed project plan | 1 | 8 | Closed | 1 | Umut | 0 | 22 | <ProjectPlan.doc>
Define schedules |  |  | Closed | 1 |  |  | 8 | <TentativeSchedule.xlsx>
Define milestones |  |  | Closed | 1 |  |  | 8
Decide on necessary resources |  |  | Closed | 1 |  |  | 6
Define roles and responsibilities | 2 | 2 | Assigned | 2 | Ezgi E. | 2 | 6
Define system-wide requirements | 2 | 3 | Assigned | 2 | Mustafa | 8 | 8 | <SystemWideRequirements.docx>
Define an initial high-level system architecture | 2 | 3 | New | 2 |  | 8 | 8
Define objects, attrbiutes, methods | 3 |  | New | 3
Form dataflow diagram | 2 |  | Closed | 2
Develop a use-case model | 2 | 5 | Verified | 1 |  | 6 | 14
Define and classify actors | 2 | 2 | Assigned | 2 | Umut | 6 | 8
Form use-case diagrams | 1 | 3 | Closed | 1 |  | 0 | 6
Define uses cases | 2 | 13 | Verified | 2 |  | 11 | 29
Make a reservation by diner | 2 |  | Closed | 1 | Ezgi E. | 0 | 8 | <UC1: Make Reservation.docx>
Manage reservation by restaurant manager | 2 |  | Closed | 1 | Tunalı | 0 | 5 | <UC2: Manage Reservations.docx>
Update/Cancel reservations by diner | 2 |  | Closed | 1 | Umut | 0 | 5 | <UC3: Update Reservation.docx>
Manage Waitlist | 2 |  | Assigned | 3 | Ezgi E. | 5 | 5
Give feedback for completed reservations | 2 |  | Assigned | 3 | Tunalı | 3 | 3
Check reservations of the new-comers, update tables and records accordingly | 2 |  | Assigned | 3 | Mustafa | 3 | 3
Define offline scenarios for internet failures | 2 | 3 | Closed (Out of Scope) | 2 |  | 8 | 8
Do the design | 2 | 8 | New | 3 |  | 22 | 22
Develop code | 2 | 21 | New | 3 |  | 65 | 65
Design interface | 2 |  | New | 3
Define data base and entity relationships | 2 |  | New | 3
Detailed architecture | 3 |  | New | 3
Involve restaurant staff to validate the system and requirements | 3
Collaborate with restaurants to integrate the system with existing systems | 3 | 5 | Assigned | 3 | Umut | 18 | 2
Define data management policies | 4 | 5 | Assigned | 3 | Ezgi E. | 65 | 11
Ensure compliance with data privacy regulations | 4 | 1 | Assigned | 3 | Tunalı | 5 | 4
Decide on how the info is handled, stored and protected | 4 | 1 | Assigned | 3 | Mustafa | 4 | 4
Collaborate with marketing team to promote the system to potential diners | 5 | 100 | New
Oversee users training by restaurant staff | 5 | 100
Monitor and report performance | 5 | 13 |  |  |  | 29 | 29
Plan for ongoing support and maintenance | 5 | 8 |  |  |  | 22 | 22
Collect feedback | 5 | 8 |  |  |  | 22 | 22
Add additional features according to collected feedback | 5 | 100
Add loyalty program to leverage the platform as a marketing tool | 5 | 100
Add layout support | 5 | 100
Integrate with google maps | 5 | 100