## ReserveWell
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Define project goals, scope, objectives and deliverable | 1 | 3 | Resolved | 1 |  | 0 | 8 | <Vision.doc>
Identify stakeholders, end users | 1 | 3 | Resolved | 1 | Tunalı | 0 | 8 | <Vision.doc>
Identify and assess potential risks | 1 | 2 | Resolved | 1 | Mustafa | 0 | 5 | <RiskList.doc>
Develop a business case | 1 | 3 | Closed | 1 |  | 0 | 8 | <Vision.doc>
Create iteration plans | 1 | 8 | Verified | 4 | Ezgi E. | 6 | 24
Define Iteration Plan 1 | 1 |  | Closed | 1 | Ezgi E. | 0 | 6 | <IterationPlan1.doc>
Define Iteration Plan 2 | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <IterationPlan2.doc>
Define Iteration Plan 3 | 2 |  | Closed | 3 | Ezgi E. | 0 | 6 | <IterationPlan3.doc>
Define Iteration Plan 4 | 3 |  | Assigned | 4 | Ezgi E. | 6 | 6
Develop a detailed project plan | 1 | 8 | Closed | 1 | Umut | 0 | 22 | <ProjectPlan.doc>
Define schedules | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Define milestones | 1 |  | Closed | 1 |  | 0 | 8 | <TentativeSchedule.xlsx>
Decide on necessary resources | 1 |  | Closed | 1 |  | 0 | 6
Define roles and responsibilities | 2 | 2 | Assigned | 2 | Ezgi E. | 2 | 6
Define system-wide requirements | 2 | 3 | Assigned | 2 | Mustafa | 8 | 8 | <SystemWideRequirements.docx>
Define an initial high-level system architecture | 2 | 3 | Verified | 2 |  | 8 | 8 | <Architecture Notebook.docx>
Define objects, attrbiutes, methods | 3 |  | New | 3 |  | 5 | 5 | <Design.docx>, <Architecture Notebook.docx>
Form dataflow diagram | 2 |  | Closed | 2 | Tunalı | 0 | 3
Develop a use-case model | 2 | 5 | Closed | 1 |  | 6 | 15 | <Use Case Diagram_ReserveWell>
Define and classify actors | 2 | 2 | Closed | 2 |  | 6 | 8
Form use-case diagrams | 1 | 3 | Closed | 1 | Tunalı | 0 | 6
Define diner uses cases | 2 | 13 | Closed | 2 |  | 11 | 29
Register | 2 |  | Closed | 2 |  |  |  | <UC1: Register by Diner.docx>
Make Reservation | 2 |  | Closed | 1 | Ezgi E. | 0 | 8 | <UC2: Make Reservation.docx>
Update Reservation | 2 |  | Closed | 1 | Umut | 0 | 5 | <UC3: Update Reservation.docx>
Exit from a Waitlist | 2 |  | Closed | 2 | Ezgi E. | 5 | 5 | <UC4: Exit From a Waitlist.docx>
Manage Notifications | 2 |  | Closed | 2 | Ezgi E. |  |  | <UC5: Manage Notifications .docx>
Rate the Restaurant | 2 |  | Closed | 2 | Ezgi E. | 3 | 3 | <UC6: Rate Restaurant.docx>
Define restaurant manager uses cases | 2 | 13 | Closed | 2 |  | 0 | 29
RegisterR | 2 |  | Closed | 2 | Ezgi E. | 0 | 6 | <UC7: Register by Restaurant Manager.docx>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC8: Display Reservations by Restaurant Manager.docx>
Manage Reservations - güncelle feedbacke göre | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC9: Manage Reservations.docx>
Edit Working Hours | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC10: Edit Working Hours.docx>
Edit Capacity | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC11: Edit Capacity.docx>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 5 | <UC12: Display Dashboards.docx>
Manage Restaurant's Waitlist | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC13: Manage Restaurant's Waitlist.docx>
Define waitstaff uses cases | 2 | 13 | Closed | 2 | Ezgi E. | 0 | 27
Register | 2 |  | Closed | 2 | Ezgi E. | 0 | 5 | <UC14: Register by Waitstaff.docx>
Display Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 6 | <UC15: Display Reservations by Waitstaff.docx>
Display Dashboards | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC12: Display Dashboards.docx>
Confirm Realized Reservations | 2 |  | Closed | 2 | Tunalı | 0 | 8 | <UC16: Confirm Realized Reservations.docx>
Support basic registering process | 1 | 5 | Assigned | 3 | Tunalı | 17 | 17
Prototype UI | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Do the design | 1 |  | Assigned | 3 | Tunalı | 5 | 5
Implement | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Test |  |  | Assigned | 3 | Tunalı | 3 | 3
Verify data flow | 1 |  | Assigned | 3 | Tunalı | 3 | 3
Support basic creating new reservation process | 2 | 8 | Verified | 2 | Umut | 3 | 24
Prototype UI | 2 |  | Closed | 2 | Umut | 0 | 5
Do the design | 2 |  | Closed | 2 | Umut | 0 | 8
Implement | 2 |  | Closed | 2 | Umut | 0 | 5
Test |  |  | Assigned | 3 | Umut | 3 | 3
Verify data flow | 2 |  | Closed | 2 | Umut | 0 | 3
Support basic managing reservations process | 2 | 13 | Assigned | 3 | Mustafa | 32 | 32
Prototype UI | 2 |  | Assigned | 3 | Mustafa | 5 | 5
Do the design | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Implement | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Test |  |  | Assigned | 3 | Mustafa | 3 | 3
Verify data flow | 2 |  | Assigned | 3 | Mustafa | 8 | 8
Support waitlist management | 2 | 13 | Assigned | 4 | Umut | 32 | 32
Prototype UI | 2 |  | Assigned | 4 | Umut | 5 | 5
Do the design | 2 |  | Assigned | 4 | Umut | 8 | 8
Implement | 2 |  | Assigned | 4 | Umut | 8 | 8
Test |  |  | Assigned | 4 | Umut | 3 | 3
Verify data flow | 2 |  | Assigned | 4 | Umut | 8 | 8
Support restaurant customizations | 2 | 5 | New | 3 |  | 19 | 19
Prototype UI | 2 |  | New | 3 |  | 3 | 3
Do the design | 2 |  | New | 3 |  | 5 | 5
Implement | 2 |  | New | 3 |  | 3 | 3
Test |  |  | New | 3 |  | 3 | 3
Verify data flow | 2 |  | New | 3 |  | 5 | 5
Support feedback infrastructure | 3 | 8 | New | 4 |  | 23 | 23
Prototype UI | 3 |  | New | 4 |  | 5 | 5
Do the design | 3 |  | New | 4 |  | 5 | 5
Implement | 3 |  | New | 4 |  | 5 | 5
Test |  |  | New | 4 |  | 3 | 3
Verify data flow | 3 |  | New | 4 |  | 5 | 5
Support data visualization | 3 | 13 | New | 3 |  | 31 | 31
Decide whether outsourcing or inhouse | 3 |  | New | 2 |  | 8 | 8
Prototype UI | 3 |  | New | 3 |  | 5 | 5
Do the design | 3 |  | New | 3 |  | 5 | 5
Implement | 3 |  | New | 3 |  | 5 | 5
Test |  |  | New | 3 |  | 3 | 3
Verify data flow | 3 |  | New | 3 |  | 5 | 5
Complete Development Work Products | 2 |  | Verified | 3
Define design artifact | 2 |  | Closed | 2
Define implementation artifact | 2 |  | Closed | 2
Define build artifact | 2 |  | New | 3
Define developer test artifact | 2 |  | Assigned | 3 | Mustafa
Define prior deployment plan | 1 | 5 | Closed | 1 | Umut | 5 | 13
Define test scenarios which are not use case specific | 2 | 8 | Assigned | 3 | Mustafa | 20 | 20
Define offline scenarios for internet failures | 2 | 3 | Closed (Out of Scope) | 2 |  | 8 | 8
Do the design | 2 | 8 | Assigned | 3 | Umut | 22 | 22
Develop code | 2 | 13 | Assigned | 3 |  | 29 | 29
Design interface | 2 |  | New | 3 |  | 8 | 8
Define data base and entity relationships | 2 |  | New | 3 |  | 8 | 8
Detailed architecture | 3 |  | New | 3 |  | 13 | 13
Involve restaurant staff to validate the system and requirements | 3 | 5 | New | 5 |  | 13 | 13
Collaborate with restaurants to integrate the system with existing systems | 3 | 5 | Assigned | 3 | Umut | 18 | 18
Define data management policies | 4 | 5 | Assigned | 4 |  | 13 | 13
Ensure compliance with data privacy regulations | 4 | 1 | Assigned | 4 |  | 5 | 4
Decide on how the info is handled, stored and protected | 4 | 1 | Assigned | 4 |  | 8 | 4
Collaborate with marketing team to promote the system to potential diners | 5 | 100 | New
Oversee users training by restaurant staff | 5 | 100 | New
Monitor and report performance | 5 | 13 | New |  |  | 29 | 29
Plan for ongoing support and maintenance | 5 | 8 | New |  |  | 21 | 21
Collect feedback | 5 | 8 | New |  |  | 21 | 21
Add additional features according to collected feedback | 5 | 100 | New
Add loyalty program to leverage the platform as a marketing tool | 5 | 100 | New
Add layout support | 5 | 100 | New
Integrate with google maps | 5 | 100 | New